## Risk Management Plan (Group 9)
Risk | Probability of occurrence | Impact | Impact level | Classification | Response types | Response description
Team member is sicked | Possible | The development could be delayed | Major | Medium | Avoid | We aim to have a work-life balance among the team members to maintain good health.
The software developed are being hacked by hackers | Unlikely | Potentially make the whole system down. | Critical | Medium | Mitigate | Host our software application on the high-security cloud server platform.
Poor time management | Likely | Possible stuck and delay | Moderate | Medium | Mitigate | Try to monitor and remind each team member to follow our planned timeline.
Data loss due to any hardware or software failure | Unlikely | Loss of work done. | Major | Medium | Avoid | Setup manual and automatic backup for all the project documents and code.
The client will request correcting some bugs or adding features, not in the sprint. | Likely | Client will be unsatisfied with bugs or regressions that may appear | Major | High | Accept | Depending on the issue size, we can do a favour to the client. But the client should know that it's a favour
Developing the wrong software functions | Possible | Possible stuck and delay | Major | Medium | Avoid | Having better communication with clients by using user surveys, prototyping, etc.
Developing the wrong user interface | Possible | May need to redesign the user interface | Critical | High | Avoid | Having better communication with clients by using user surveys, prototyping, etc.
Real-time performance problems | Possible | Bad user experience | Moderate | Medium | Mitigate | Software tuning and server optimisation.
Not enough communication within the team members | Likely | Misunderstanding issues may occur | Major | High | Mitigate | to communicate with each other by all means actively
Other team members will be on vacation or leave for some reason | Possible | Possible stuck and delay | Major | Medium | Mitigate | We may need to re-assign the tasks or recruit another member.
Late changes to requirements | Unlikely | Possible some re-work | Moderate | Medium | Escalate | Discuss with key stakeholders if necessary.
Note on D1: 1- Trivial: It is merely an inconvenience. Have no effect on the project. 2- Minor: Would cause only a small cost and schedule increase. Requirements would still be achieved. 3- Moderate: Would cause moderate cost and schedule increases. Important requirements would still be met. 4- Major: Would cause major cost and schedule increases. Would impact customer satisfaction. 5- Critical: Inability to achieve minimum acceptable requirements. Would cause project to pause or fail.
Note on E1: Auto filled ------------------------- Low: No need to elaborate a response. This is an accepted risk Medium: Prepare a quick response. Watch triggers. High: Prepare a detailed response. Watch triggers very closely.
Note on F1: Escalate: Escalate the risk to higher authority: PMO, CEO, Client, etc. Avoid: Eliminate cause of risk Mitigate: Reduce probability or impact of risk Accept: Contingency plan for risk Transfer: Have third party take on responsibility for risk

## Probability and Impact matrix
Probability and Impact matrix
Prob. \ Impact | Trivial | Minor | Moderate | Major | Critical
Rare: This will probably never happen | Low | Low | Low | Medium | Medium
Unlikely: Do not expect it to happen | Low | Low | Medium | Medium | Medium
Possible: Might happen | Low | Medium | Medium | Medium | High
Likely: Will probably happen | Medium | Medium | Medium | High | High
Very likely: Will undoubtedly happen | Medium | Medium | High | High | High
Classification | Description
Low | No need to elaborate on a response. This is an accepted risk.
Medium | Prepare a quick response. Watch triggers.
High | Prepare a detailed response. Watch triggers closely.
Response types | Description
Escalate | Escalate the risk to a higher authority: Client, etc.
Avoid | Eliminate the cause of risk
Mitigate | Reduce the probability or impact of risk
Accept | Contingency plan for risk
Transfer | Have a third party take on responsibility for risk
Note on B2: It is merely an inconvenience. Have no effect on the project.
Note on C2: Would cause only a small cost and schedule increase. Requirements would still be achieved.
Note on D2: Would cause moderate cost and schedule increases. Important requirements would still be met.
Note on E2: Would cause major cost and schedule increases. Would impact customer satisfaction.
Note on F2: Inability to achieve minimum acceptable requirements. Would cause project to pause or fail.